## WBS
| WSS - UI - WBS | [11 empty] | Month: | 2 | [21 empty] | 3 | [30 empty] | 4 | [29 empty] | 5
No. | Task Name |  |  |  | Task Description | Estimate | Assignee | Start Actual date | End Actual date | Start Scheduled date | End Scheduled date | Progress | Status | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31
[14 empty] | 44599 | 44600 | 44601 | 44602 | 44603 | 44604 | 44605 | 44606 | 44607 | 44608 | 44609 | 44610 | 44611 | 44612 | 44613 | 44614 | 44615 | 44616 | 44617 | 44618 | 44619 | 44620 | 44621 | 44622 | 44623 | 44624 | 44625 | 44626 | 44627 | 44628 | 44629 | 44630 | 44631 | 44632 | 44633 | 44634 | 44635 | 44636 | 44637 | 44638 | 44639 | 44640 | 44641 | 44642 | 44643 | 44644 | 44645 | 44646 | 44647 | 44648 | 44649 | 44650 | 44651 | 44652 | 44653 | 44654 | 44655 | 44656 | 44657 | 44658 | 44659 | 44660 | 44661 | 44662 | 44663 | 44664 | 44665 | 44666 | 44667 | 44668 | 44669 | 44670 | 44671 | 44672 | 44673 | 44674 | 44675 | 44676 | 44677 | 44678 | 44679 | 44680 | 44681 | 44682 | 44683 | 44684 | 44685 | 44686 | 44687 | 44688 | 44689 | 44690 | 44691 | 44692 | 44693 | 44694 | 44695 | 44696 | 44697 | 44698 | 44699 | 44700 | 44701 | 44702 | 44703 | 44704 | 44705 | 44706 | 44707 | 44708 | 44709 | 44710 | 44711 | 44712
1 | Research framework |  |  |  |  | 5 |  |  |  | 2022-02-07 | 2022-02-17
2 | Create Test plan |  |  |  |  | 8 |  |  |  | 2022-02-09 | 2022-02-17
3 | Setting environment |  |  |  |  | 1 |  |  |  | 2022-02-21 | 2022-02-25
4 | Create Document for setup environment & setup source code |  |  |  |  | 1 |  |  |  | 2022-02-21 | 2022-02-25
5 | Create Document for creating test cases |  |  |  |  | 1 |  |  |  | 2022-02-21 | 2022-02-25
6 | Service Manager Menu |  |  |  |  | 91 |  | 2022-02-18 | 2022-03-09 | 2022-02-21 | 2022-05-06 | 0%
7 |  | Login |  |  |  | 5 |  | 2022-02-18 | 2022-02-18 | 2022-02-21 | 2022-03-04 | 0%
8 |  |  |  | Layout | [7 empty] | 0%
9 |  |  |  | Login functionalities | [7 empty] | 0%
10 |  |  | Design test cases |  |  | 1 |  | 2022-02-18 | 2022-02-18 | 2022-02-21 | 2022-02-21 | 0%
11 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-02-22 | 2022-02-22 | 0%
12 |  |  | Create and run automated test scripts |  |  | 2 |  |  |  | 2022-02-22 | 2022-02-23 | 0%
13 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-02-28 | 2022-03-04 | 0%
14 |  | Dashboard |  |  |  | 9 |  | 2022-03-03 | 2022-03-03 | 2022-02-22 | 2022-03-11 | 0%
15 |  |  |  | Layout | [7 empty] | 0%
16 |  |  |  | Dashboard Page link | [7 empty] | 0%
17 |  |  |  | Filter based on Toggle Backlog/Assigned/On Hold/ In Progress/ Work Completed | [7 empty] | 0%
18 |  |  |  | Filter based on location | [7 empty] | 0%
19 |  |  |  | Search function | [7 empty] | 0%
20 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
21 |  |  |  | Redirect to the WO detail page | [7 empty] | 0%
22 |  |  |  | Redirect to New WO page | [7 empty] | 0%
23 |  |  |  | Open Jobsite popup | [7 empty] | 0%
24 |  |  |  | Open Assign Mechanic popup | [7 empty] | 0%
25 |  |  |  | Open setting popup | [7 empty] | 0%
26 |  |  |  | Open Manage Views popup | [7 empty] | 0%
27 |  |  |  | Filter based on Manage Views | [7 empty] | 0%
28 |  |  |  | Pagging | [7 empty] | 0%
29 |  |  | Design test cases |  |  | 2 |  | 2022-03-03 | 2022-03-03 | 2022-02-22 | 2022-02-23 | 0%
30 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-02-24 | 2022-02-25 | 0%
31 |  |  | Create and run automated test scripts |  |  | 5 |  |  |  | 2022-02-24 | 2022-03-02 | 0%
32 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-03-07 | 2022-03-11 | 0%
33 |  | Function XXA |  |  |  | 15 |  | 2022-03-09 | 2022-03-09 | 2022-02-24 | 2022-03-17 | 0%
34 |  |  |  | Initial layout | [7 empty] | 0%
35 |  |  |  | Layout based on Bill Type | [7 empty] | 0%
36 |  |  |  | Layout based on Claim Type | [7 empty] | 0%
37 |  |  |  | Work Order Page link | [7 empty] | 0%
38 |  |  |  | Open Select equipment popup | [7 empty] | 0%
39 |  |  |  | Open Jobsite popup | [7 empty] | 0%
40 |  |  |  | Open Driver's License | [7 empty] | 0%
41 |  |  |  | Open setting popup | [7 empty] | 0%
42 |  |  |  | Adding Notes function | [7 empty] | 0%
43 |  |  |  | Adding Attachment function | [7 empty] | 0%
44 |  |  |  | Viewing Attachment function | [7 empty] | 0%
45 |  |  |  | Adding Labor function | [7 empty] | 0%
46 |  |  |  | Adding Parts function | [7 empty] | 0%
47 |  |  |  | Adding Misc function | [7 empty] | 0%
48 |  |  |  | Editing Steps function | [7 empty] | 0%
49 |  |  |  | Printing Steps function | [7 empty] | 0%
50 |  |  |  | Adding Deficiencies function | [7 empty] | 0%
51 |  |  |  | Open Trace log popup | [7 empty] | 0%
52 |  |  |  | Save a new Work Order | [7 empty] | 0%
53 |  |  | Design test cases |  |  | 3 |  | 2022-03-09 | 2022-03-09 | 2022-02-24 | 2022-02-28 | 0%
54 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-01 | 2022-03-03 | 0%
55 |  |  | Create and run automated test scripts |  |  | 10 |  |  |  | 2022-03-03 | 2022-03-16 | 0%
56 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-03-17 | 2022-03-17 | 0%
57 |  | Function XXA |  |  |  | 12 |  |  |  | 2022-03-01 | 2022-04-01 | 0%
58 |  |  |  | Initial layout | [7 empty] | 0%
59 |  |  |  | Layout based on Bill Type | [7 empty] | 0%
60 |  |  |  | Layout based on Claim Type | [7 empty] | 0%
61 |  |  |  | Work Order Page link | [7 empty] | 0%
62 |  |  |  | Open Select equipment popup | [7 empty] | 0%
63 |  |  |  | Open Jobsite popup | [7 empty] | 0%
64 |  |  |  | Open Driver's License | [7 empty] | 0%
65 |  |  |  | Open setting popup | [7 empty] | 0%
66 |  |  |  | Adding Notes function | [7 empty] | 0%
67 |  |  |  | Adding Attachment function | [7 empty] | 0%
68 |  |  |  | Viewing Attachment function | [7 empty] | 0%
69 |  |  |  | Adding Labor function | [7 empty] | 0%
70 |  |  |  | Adding Parts function | [7 empty] | 0%
71 |  |  |  | Adding Misc function | [7 empty] | 0%
72 |  |  |  | Editing Steps function | [7 empty] | 0%
73 |  |  |  | Printing Steps function | [7 empty] | 0%
74 |  |  |  | Adding Deficiencies function | [7 empty] | 0%
75 |  |  |  | Open Trace log popup | [7 empty] | 0%
76 |  |  |  | Update and save an existed Work Order | [7 empty] | 0%
77 |  |  | Design test cases |  |  | 3 |  |  |  | 2022-03-01 | 2022-03-03 | 0%
78 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-04 | 2022-03-11 | 0%
79 |  |  | Create and run automated test scripts |  |  | 7 |  |  |  | 2022-03-17 | 2022-03-25 | 0%
80 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-03-28 | 2022-04-01 | 0%
81 |  | Function XXA |  |  |  | 7 |  |  |  | 2022-03-04 | 2022-04-08 | 0%
82 |  |  |  | Layout | [7 empty] | 0%
83 |  |  |  | Assignment Page link | [7 empty] | 0%
84 |  |  |  | Search function | [7 empty] | 0%
85 |  |  |  | Filter based on location | [7 empty] | 0%
86 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
87 |  |  |  | Redirect to the WO detail page | [7 empty] | 0%
88 |  |  |  | Redirect to New WO page | [7 empty] | 0%
89 |  |  |  | Open Jobsite popup | [7 empty] | 0%
90 |  |  |  | Open Manage Views | [7 empty] | 0%
91 |  |  |  | Open setting popup | [7 empty] | 0%
92 |  |  |  | Open Manage Views popup | [7 empty] | 0%
93 |  |  |  | Filter based on Manage Views | [7 empty] | 0%
94 |  |  |  | Filter based on Mechanic | [7 empty] | 0%
95 |  |  |  | Pagging | [7 empty] | 0%
96 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-04 | 2022-03-07 | 0%
97 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-08 | 2022-03-11 | 0%
98 |  |  | Create and run automated test scripts |  |  | 3 |  |  |  | 2022-03-28 | 2022-03-30 | 0%
99 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-03-31 | 2022-04-08 | 0%
100 |  | Function XXA |  |  |  | 9 |  |  |  | 2022-03-08 | 2022-04-15 | 0%
101 |  |  |  | Layout | [7 empty] | 0%
102 |  |  |  | Mechanic Page link | [7 empty] | 0%
103 |  |  |  | Start Attendance | [7 empty] | 0%
104 |  |  |  | Start Work order | [7 empty] | 0%
105 |  |  |  | Search based on WO stage | [7 empty] | 0%
106 |  |  |  | Search based on Parts stage | [7 empty] | 0%
107 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
108 |  |  |  | Redirect to the WO detail page | [7 empty] | 0%
109 |  |  |  | Redirect to New WO page | [7 empty] | 0%
110 |  |  |  | Open Jobsite popup | [7 empty] | 0%
111 |  |  |  | Adding Parts function | [7 empty] | 0%
112 |  |  |  | Adding Steps function | [7 empty] | 0%
113 |  |  |  | Adding Deficiencies function | [7 empty] | 0%
114 |  |  |  | Adding Attachment function | [7 empty] | 0%
115 |  |  |  | Adding Notes function | [7 empty] | 0%
116 |  |  |  | Open Assign Mechanic popup | [7 empty] | 0%
117 |  |  |  | In Progress/Assignment tab | [7 empty] | 0%
118 |  |  |  | Pagging | [7 empty] | 0%
119 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-08 | 2022-03-09 | 0%
120 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-10 | 2022-03-11 | 0%
121 |  |  | Create and run automated test scripts |  |  | 5 |  |  |  | 2022-03-31 | 2022-04-06 | 0%
122 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-04-07 | 2022-04-15 | 0%
123 |  | Function XXA |  |  |  | 7 |  |  |  | 2022-03-10 | 2022-04-22 | 0%
124 |  |  |  | Layout | [7 empty] | 0%
125 |  |  |  | In Progress Page link | [7 empty] | 0%
126 |  |  |  | Search function: location, Advanced filter | [7 empty] | 0%
127 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
128 |  |  |  | Redirect to the WO detail page | [7 empty] | 0%
129 |  |  |  | Redirect to New WO page | [7 empty] | 0%
130 |  |  |  | Open Jobsite popup | [7 empty] | 0%
131 |  |  |  | Open setting popup | [7 empty] | 0%
132 |  |  |  | Pagging | [7 empty] | 0%
133 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-10 | 2022-03-11 | 0%
134 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-14 | 2022-03-18 | 0%
135 |  |  | Create and run automated test scripts |  |  | 3 |  |  |  | 2022-04-07 | 2022-04-11 | 0%
136 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-04-12 | 2022-04-22 | 0%
137 |  | Function XXA |  |  |  | 7 |  |  |  | 2022-03-14 | 2022-04-22 | 0%
138 |  |  |  | Layout | [7 empty] | 0%
139 |  |  |  | Quote Page link | [7 empty] | 0%
140 |  |  |  | Filter based on Toggle Pending/Rejected/ In review/Approved/Converted/Canceled | [7 empty] | 0%
141 |  |  |  | Filter based on location | [7 empty] | 0%
142 |  |  |  | Search function | [7 empty] | 0%
143 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
144 |  |  |  | Redirect to the Quote detail page | [7 empty] | 0%
145 |  |  |  | Redirect to New Quote page | [7 empty] | 0%
146 |  |  |  | Open Jobsite popup | [7 empty] | 0%
147 |  |  |  | Open setting popup | [7 empty] | 0%
148 |  |  |  | Open Manage Views popup | [7 empty] | 0%
149 |  |  |  | Filter based on Manage Views | [7 empty] | 0%
150 |  |  |  | Pagging | [7 empty] | 0%
151 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-14 | 2022-03-15 | 0%
152 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-16 | 2022-03-18 | 0%
153 |  |  | Create and run automated test scripts |  |  | 3 |  |  |  | 2022-04-12 | 2022-04-14 | 0%
154 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-04-15 | 2022-04-22 | 0%
155 |  | Function XXA |  |  |  | 9 |  |  |  | 2022-03-16 | 2022-04-30 | 0%
156 |  |  |  | Initial layout | [7 empty] | 0%
157 |  |  |  | Layout based on Bill Type | [7 empty] | 0%
158 |  |  |  | Layout based on Claim Type | [7 empty] | 0%
159 |  |  |  | New Quote Page link | [7 empty] | 0%
160 |  |  |  | Open Select equipment popup | [7 empty] | 0%
161 |  |  |  | Open Jobsite popup | [7 empty] | 0%
162 |  |  |  | Open Driver's License | [7 empty] | 0%
163 |  |  |  | Open setting popup | [7 empty] | 0%
164 |  |  |  | Adding Notes function | [7 empty] | 0%
165 |  |  |  | Adding Attachment function | [7 empty] | 0%
166 |  |  |  | Viewing Attachment function | [7 empty] | 0%
167 |  |  |  | Adding Parts function | [7 empty] | 0%
168 |  |  |  | Adding Misc function | [7 empty] | 0%
169 |  |  |  | Open Trace log popup | [7 empty] | 0%
170 |  |  |  | Save a new Quote | [7 empty] | 0%
171 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-16 | 2022-03-17 | 0%
172 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-18 | 2022-03-25 | 0%
173 |  |  | Create and run automated test scripts |  |  | 5 |  |  |  | 2022-04-15 | 2022-04-21 | 0%
174 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-04-22 | 2022-04-30 | 0%
175 |  | Function XXA |  |  |  | 9 |  |  |  | 2022-03-18 | 2022-05-06 | 0%
176 |  |  |  | Initial layout | [7 empty] | 0%
177 |  |  |  | Layout based on Bill Type | [7 empty] | 0%
178 |  |  |  | Layout based on Claim Type | [7 empty] | 0%
179 |  |  |  | New Quote Page link | [7 empty] | 0%
180 |  |  |  | Open Select equipment popup | [7 empty] | 0%
181 |  |  |  | Open Jobsite popup | [7 empty] | 0%
182 |  |  |  | Open Driver's License | [7 empty] | 0%
183 |  |  |  | Open setting popup | [7 empty] | 0%
184 |  |  |  | Adding Notes function | [7 empty] | 0%
185 |  |  |  | Adding Attachment function | [7 empty] | 0%
186 |  |  |  | Viewing Attachment function | [7 empty] | 0%
187 |  |  |  | Adding Parts function | [7 empty] | 0%
188 |  |  |  | Adding Misc function | [7 empty] | 0%
189 |  |  |  | Open Trace log popup | [7 empty] | 0%
190 |  |  |  | Convert to WO | [7 empty] | 0%
191 |  |  |  | Cancel a quote | [7 empty] | 0%
192 |  |  |  | Update and save an existed quote | [7 empty] | 0%
193 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-18 | 2022-03-21 | 0%
194 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-22 | 2022-03-25 | 0%
195 |  |  | Create and run automated test scripts |  |  | 5 |  |  |  | 2022-04-22 | 2022-04-28 | 0%
196 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-04-29 | 2022-05-06 | 0%
197 |  | Function XXA |  |  |  | 7 |  |  |  | 2022-03-22 | 2022-05-06 | 0%
198 |  |  |  | Layout | [7 empty] | 0%
199 |  |  |  | Close and Bill Page link | [7 empty] | 0%
200 |  |  |  | Toggle Work complete / Closed | [7 empty] | 0%
201 |  |  |  | Search function | [7 empty] | 0%
202 |  |  |  | Redirect to the equipment page | [7 empty] | 0%
203 |  |  |  | Redirect to the Quote detail page | [7 empty] | 0%
204 |  |  |  | Open Jobsite popup | [7 empty] | 0%
205 |  |  |  | Open setting popup | [7 empty] | 0%
206 |  |  |  | Open Manage Views | [7 empty] | 0%
207 |  |  |  | Search Manage Views | [7 empty] | 0%
208 |  |  |  | Pagging | [7 empty] | 0%
209 |  |  | Design test cases |  |  | 2 |  |  |  | 2022-03-22 | 2022-03-23 | 0%
210 |  |  | Review and update test cases |  |  | 1 |  |  |  | 2022-03-24 | 2022-03-25 | 0%
211 |  |  | Create and run automated test scripts |  |  | 3 |  |  |  | 2022-04-29 | 2022-05-03 | 0%
212 |  |  | Review and update automated test scripts |  |  | 1 |  |  |  | 2022-05-04 | 2022-05-06 | 0%